## 2014_15 Plan
Mimaansa AIP
Priority Area | Goal - What do we have to do this year | Outcome - Why do we want it | Activity - How do we do it | Q1 | Q2 | Q3 | Q4 | Deadline | Resources | Responsibe Person | Status | Comments
Quality & Cost Efficiency | Goal 1: Launch the teacher training program | Outcome 1: Have a replicable curriculum for the teacher training | Activity 1.1: Develop the curriculum for teacher training |  |  |  |  | End of June |  | Pooja
|  |  | Activity 1.2: Identify who is going to lead the training | [6 empty] | Pooja
|  |  | Activity 1.3: Train the staff | [6 empty] | Pooja
|  |  | Activity 1.4: Validate teacher training curriculum | 3 teacher training institutes | 2 organizations | Finalize the validation |  |  |  | Pooja
Activity 1.5: Launch teacher training
| Goal 2: Standardize the existing program | Outcome 2: Replicability of program | Activity 2.1: Formalize the process manual and methodology |  |  |  |  | 15th May |  | Pooja
|  |  | Activity 2.2: Create a lesson plan bank | [6 empty] | Pooja
|  |  | Activity 2.3: Review and update lesson plans every two months |  | Lesson plans reviewed | Lesson plans reviewed | Lesson plans reviewed
| Goal 3: Reach out to 650 students | Outcome 3: Increased beneficiary number and reach | Activity 3.1: Improve current screening process |  |  |  |  | End of May |  | Pooja
|  |  | Activity 3.2: Engage with 2 new schools | 1st school |  | 2nd school |  | End of May |  | Pooja
Successful Outcomes | Goal 1: Build a comprehensive M&E system (improve the current one) | Outcome 1: 45% increase in the learning of students | Activity 1.1: Gap analysis |  |  |  |  | End of June |  | Pooja/Atma PM
|  |  | Activity 1.2: Create action plan |  |  |  |  | End of June |  | Pooja/Atma PM
|  |  | Activity 1.3: Define reporting format | [6 empty] | Pooja/Atma PM
Activity 1.4: Develop data base management system
|  |  | Activity 1.5: Launch M&E system |  |  | System launched
Activity 1.6: Collect data
External Recognition | Goal 1: Curriculum certification and one affiliate partner | Outcome 1: Certified Curriculum | Activity 1.1: Map special education players
Activity 1.2: Write proposal for engagement with selected organizations
Activity 1.3: Design an affiliation program
Activity 1.4: Launch affiliation program
Funding | Goal 1: Raise 42 lakhs through corporate partnerships | Outcome 1: 2 corporate tie ups established | Activity 1.1: List corporates in Powai/Thane with CSR programme with focus in education | [6 empty] | Pooja/Atma Associate
|  |  | Activity 1.2: Create collaterals and proposal | [6 empty] | Pooja/Atma Associate
|  |  | Activity 1.3: Set-up pricing model for program | [6 empty] | Pooja/Atma Associate
|  |  | Activity 1.4: Send out proposals |  | 1st corporate partner | 2nd corporate partner
Talent & Partner Acquisition and Retention | Goal 1: Government involvement | Outcome 1: Government bodies are active partners | Activity 1.1: Review the communication schedule with government | [6 empty] | Pooja
|  |  | Activity 1.2: Send regular reports and organize visits | 1 report | 1 report | 1 report | 1 report |  |  | Pooja
| Goal 2: Hire 4 special educators and 1 program manager | Outcome 2: Specialized and effective team | Activity 2.1: Tie up with education institutions which offer courses on special educations | 1st tie-up | 2nd tie-up |  |  |  |  | Pooja
|  |  | Activity 2.2: Sign up with forums | [6 empty] | Pooja
|  |  | Activity 2.3: Set up recruitment process | [6 empty] | Pooja/Atma Associate
|  |  | Activity 2.4: Recruit staff members | 2 Special Ed | 1 Project Manager | 2 Special Ed |  |  |  | Pooja/Atma Associate
|  |  | Activity 2.5: Set up induction process and induce new staff members | Induction process in place | [5 empty] | Pooja/Atma Associate